## Sheet1
Poornima College of Engineering
Department of Information Technology
Product Backlog (Project-II: 2018-19)
Epic | Sprint | User Story Role | User Story Name | Story Details | Tasks Items | Analyst / Prep work | Dev. Estimate | QA | Total User Story Hours
Emergency Alarm | 1 | Attendant | Make Emergency call | There is an attendant for every victim. The emergency call has to be made by the attendant by a click on ‘Emergency call’ button. | 1. Obtain the geographical location of the victim using GPS. 2. Define computeDistance() function for calculating the distance between the hospitals and the accident’s location. | 10 | 45 | 2 | 57
Emergency Alarm | 2 | Admin | Developing Database | A database will be created which will be storing the hospitals details and will generate the hospital id for each of them. | 1. Create the database on Firbase. 2. Storing the Top 5 Hospitals in an array with minimum distance from accident location sorted on increasing distance. 3. Generate the hospital_id for every hospital stored in the database. | 10 | 55 | 3 | 68
Emergency Alarm | 3 | Admin | Designing GUI | A web application for the hospital side will be made in order to accept or reject the ambulance request by loging in into it. | 1. Develop the Graphical User Interface of web application for the hospital. 2. Test the GUI of created web application over it's test cases. 3. Test the GUI of the android application. | 10 | 45 | 3 | 58
Emergency Alarm | 4 | Hospital | Provide Ambulance | The selected hospital must send the ambulance along with the driver’s detail to the attendant via application. | 1. Login into the application generated using the generated user id and mobile number of the hospital. 2. Accepting the request for ambulance by clicking on the accept button present on the web application. 3. Prioritizing the hospital on the basis of First Come First Serve. 4. Share the details of ambulance and it's driver with the application. 5. Provide the ambulance as backup when required. | 10 | 55 | 4 | 69
Emergency Alarm | 5 | Attendant | Tracking Ambulance | The attendant must be able to view the details of driver along with tracking the ambulance’s location. | 1. View the details of ambulance driver. 2. Track the ambulance using GPS. 3. View the ambulance number. | 10 | 45 | 2 | 57
Emergency Alarm | 6 | Municipal Corporation Representative (MCR) | Generating weekly report | Application must be able to generate the weekly report and send it to municipality corporation. | 1. Able to access the weekly report generated by the application. | 8 | 33 | 2 | 43
Total | [5 empty] | 58 | 278 | 16 | 352
Signature (Project Guide) |  |  |  | Signature (Scrum Master) |  | Signature (Project Coordinator)